## task and timeline
Sauce & Spoon Project Plan
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [5 empty] | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
[8 empty] | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29
1 | Milestone: Tablets received
| Generate quotes and review costs |  | 2025-04-23 | 2025-03-06 | 14
| Create contracts and statements of work for vendors | Use past contracts for boilerplate | 2025-03-07 | 2025-03-12 | 5
| Order tablets | Shipping updated to ~10 days | 2025-03-13 | 2025-03-23 | 10
2 | Milestone: Training complete
| Manager training planning |  | 2025-03-24 | 2025-03-29 | 5
| Manager training | One day event | 2025-03-30 | 2025-03-31 | 1
| GM meeting with staff regarding buy-in | Let Gilly plan this | 2025-04-01 | 2025-04-01 | 1
| Waitstaff training planning |  | 2025-04-02 | 2025-04-07 | 5
| Waitstaff training | One day event | 2025-04-08 | 2025-04-08 | 1
3 | Milestone: Tablet installation complete
| Book an electrician to install the tablets/wiring | Reference from Deanna | 2025-04-09 | 2025-04-17 | 8
| Install working tablets in the bar area at the Downtown restaurant locations |  | 2025-04-18 | 2025-04-18 | 1
| Install working tablets in the bar area at the North restaurant locations |  | 2025-04-19 | 2025-04-19 | 1
| Sync tablet software with POS | Need to update the POS system | 2025-04-20 | 2025-04-27 | 7
4 | Milestone: Launch Day complete
| Create a launch day plan: staffing, troubleshooting, etc. |  | 2025-04-28 | 2025-05-18 | 20
| Upload branding to tablets | Connect the marketing team to Terrific Tablets | 2025-05-19 | 2025-05-29 | 10
| Load menus into the tablets | Waiting on Carter | 2025-05-30 | 2025-05-06 | 7
| Include messaging about payment security on the tablet | Uploading text | 2025-06-07 | 2025-06-07 | 1
| Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  | 2025-06-08 | 2025-06-21 | 14
| Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 2025-06-21 | 2025-07-04 | 13
| Create and implement a post-dining survey to assess customer satisfaction |  | 2025-07-05 | 2025-07-08 | 3
| Test run planning |  | 2025-07-08 | 2025-07-18 | 10
| Test run | One day event | 2025-07-19 | 2025-07-19 | 1
| Launch day | One day event | 2025-07-20 | 2025-07-20 | 1

## stakeholder analysis
Stakeholder | Role | Interest/Expectations
Omar Mubarak (Owner & CEO) | Strategic leader; ensures long-term profitability & brand reputation | Wants projects that align with mission & deliver measurable ROI
Deanna Coleman (Director of Operations) | Oversees day-to-day operations & major initiatives | Achieve operational efficiency, sales growth, and service excellence
Carter Ward (Executive Chef) | Oversees all kitchen operations & menu vision | Reduce food waste, maintain quality, avoid kitchen disruption
Gilly Tyson (GM – North) | Manages pilot location (North), leads FOH & customer satisfaction | Wants faster service, happy customers, minimal FOH disruption
Alex Schmidt (GM – Downtown) | Manages pilot location (Downtown) | Wants higher appetizer/drink sales, reduced waste, smooth integration
Nia Williams (GM – Waterfront) | Not part of pilot, but potential future rollout site | Observing pilot for possible adoption
Zane Dutchman (Kitchen Manager – North) | Oversees BOH at North location | Wants efficient workflows, cost control, and reduced waste
Larissa Stein (Kitchen Manager – Downtown) | Oversees BOH at Downtown location | Wants smooth operations, efficiency, and cost control
Seydou Diallo (Restaurant Technology Consultant) | Advises on tablet selection, integration, and tech issues | Wants smooth, successful launch to build credibility
Restaurant Staff (FOH & BOH) | Operate tablets daily | Want easy-to-use system, minimal disruption
Customers (Bar Area) | End users of tablets | Expect fast, accurate, enjoyable ordering experience
Stakeholder | Influence/Power | Support Level | Engagement Strategy
Omar Mubarak (Owner & CEO) | High | Medium-High | Keep informed with executive summaries; focus on ROI and brand benefits; involve in milestone reviews
Deanna Coleman (Director of Operations) | High | High | Weekly updates; involve in decision-making on scope, budget, and milestones
Carter Ward (Executive Chef) | High | Medium | Early involvement in BOH impact discussions; use Zane & Larissa to liaise
Gilly Tyson (GM – North) | Medium | High | Frequent check-ins; involve in staff training and location-specific adjustments
Alex Schmidt (GM – Downtown) | Medium | High | Frequent check-ins; involve in sales data review and operational tweaks
Nia Williams (GM – Waterfront) | Low | Medium | Keep informed; share pilot results and lessons learned
Zane Dutchman (Kitchen Manager – North) | Medium | Medium | Direct engagement for operational tweaks; gather feedback regularly
Larissa Stein (Kitchen Manager – Downtown) | Medium | Medium | Direct engagement; involve in testing order flow changes
Seydou Diallo (Restaurant Technology Consultant) | Medium | High | Include in vendor meetings; consult on technical issues early
Restaurant Staff (FOH & BOH) | Low | low | Hands-on training, support, and clear communication
Customers (Bar Area) | Low | Variable | Gather feedback, promote ease-of-use benefits

## quality assurance
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
customer satisfaction | average ticket time: appetizer=8=min; entress=12min | how can we improve ticket times? | average ticket time | TRUE
customer satisfaction | check out time < 1min | are customer satisfied with the checkout process? | check out ime | TRUE
customer satisfaction | technical issues <5% reported | how can we improve customer's ability to use the tablet | techinal issue reported | TRUE
customer satisfaction | customer satisfaction >98% | should we continue using tablets | order accuracy of tablets vs servers | TRUE
customer satisfaction | wait time <10% | how canwe improve wait times | reported wait times | TRUE
customer satisfaction | working tablet > 100% | do all the tablets are working? | techinal issue reported | TRUE

## Survey Questions
Survey Questions
Quality Standards |  |  |  | Question answer options
Criteria/Description | evaluation question | Survey question | Question type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time: apps=8min; entrees=12-15min | How can we improve ticket times? | how much time it took for your order to come to you | open ended question
|  | what did you order ? | multiple choice | only appetizer | only entrees | included both entrees and appetizer
|  | Did you use the coupon for ordering appetizer? | YES or NO | YES | NO
Check-out time: >1min | Are customers satisfied with checkout processes? | how much time it took for your to checkout? | open ended question
|  | How much do you rate on a scale of 1 to 5 your checkout process(1 being poor and 5 being excelent) | scaled question | 1 | 2 | 3 | 4 | 5
Technical issues: >5% reported | How can we improve customers' ability to use the tablets? | did you face any technical issue while ordering? | YES or NO | YES | NO
|  | How much would ypu rate your experience of ordering on the tablet (from 1 to 5) | scaled question | 1 | 2 | 3 | 4 | 5
Order accuracy: 100% | Should we continue using the tablets? | did you recieved the correct order? | True or False | TRUE | FALSE
Wait time: >10min | How can we improve wait times for customers? | have you visited the Restaurant before? | YES or NO | YES | NO
|  | Has the waiting time reduced in comparison to previous experience | YES or NO | YES | NO
|  | How much time did you wait before you were ready to place the order? | open ended question
Customer Satisfaction | Has the overall customer satisfaction increased? | How would rate this experience as compare to traditional servers | scaled | 1 | 2 | 3 | 4 | 5
|  | How much would you rate your overall tablet experience | scaled | 1 | 2 | 3 | 4 | 5
|  | on average how much time your dinner took? | scaled | 0-20min | 20-40min | 40-60 min | 60-80 min | 80+

## retrospective ideas
RETROSPECTIVE IDEAS
Feedback From: | Type: | Description: | Evidence: | Actions:
Project team | Needs improvement | average waiting time | 74% customer had to wait for more than 15 minutes to get a table | The food needs to be prepared correctly so it does not go back in the ktichen again
Project team | Needs improvement | techincal issue regarding ticket accuracy | different customers reported glitches in the tablet | checking the tablets before they are ready for the service and changing the tablet between the customers if there is a technical issue
Project team | Needs improvement | kithcen opeartations improvement | 28% of the customer reported an issue with their order | kitchen staff to be trained for producing better results.
Project team | Went well | at the downtown location no techincal issues reported regarding tablet | 88% customer did not have a technical issue with their tablet | The tablets need to be checked before the service to avoid technical issue
Customers | Needs improvement | long waiting time | 74% customer had to wait for more than 15 min to get a table | Kitchen prepared a single order twice due to customer sending them back
Project team | Went well | tickets came through smoothly and were easy to keep track of | The tablet easily navigated orders and the kitchen staff found it easy to handle | Set up a meeting to discuss the matter separately
Customers | Needs improvement | kitchen did not prepare their food correctly | 28% customer reported that their food was not properly prepared | Meeting has been set up for better training of back of the kitchen staff
Project team | Went well | the food came out on time | 86% voted that their food came out before 30 min | the time of food can be reduced
Customers | Went well | Customer had a good experience at the dinner | 72% people either had a good or great experience | The food was delivered to them on time and the had good ecperience with the tablet
Customers | Went well | checkout process was smooth | 82% people found out checkout process was quick smooth and easy
Customers | Went well | food was delivered to them at good speed | 86% had their food within 30 minutes
Customers | Needs improvement | technical glitches with the tablet | customer review "the tablet froze couple of times" | Saydou is working with solutions on the tablet