## Slide 1
Milestone :
Restaurant tablet pilot launched in Bar areas
Tablet Pilot Findings
Milestone :
Restaurant tablet pilot launched in Bar areas

## Slide 2
SUMMARY
We successfully launched the tabletop tablets for ordering at the bar area of the two target locations of the restaurant
50 Guests were given the survey to collect feedback and data points in the launch of the tablets.

## Slide 3
OVERVIEW
The team intended to measure the performance of the changes and impact made by installation of the tablet which include:
Average wait time
Table turnover time
Average checkout time with the tablet
Impact on correctness in the order
Ease of use of tablet
Level of training of the wait staff
Technical issue of the tablet

## Slide 4
FINDINGS
Positive experience of people with the tablet indicated by 72% giving a positive feedback
Wait staff was trained well as 90% of the customer were satisfied with the guidance provided by them while using the tablet
Check out process with tablet received a positive feedback with 82%

## Slide 5
#1 RECOMMENDATION
Survey findings: Average waiting time didn’t decrease
Recommendation: Work with GMs on speeding up the staff and kitchen staff.

## Slide 6
#2 RECOMMENDATION
Survey findings: Orders were not prepared correctly.
Recommendation: Work with executive chef regarding the issue for better preparation of the order.